## Estimating & Buidling Sample
ESTIMATING & BUDGETING WORKSHEET with Sample Data
DESCRIPTION | SUBCONTRACTOR/CONTRACTOR | ESTIMATED COAST |  |  | ACTUAL COST | VARIANCE | CURRENT PAID | AMOUNT DUE
|  | LABOR | MATERIALS | TOTAL
GENERAL REQUIRMENTS
Plans and Specifications |  |  |  | 0 |  |  |  | 0
Plan Review |  |  |  | 0 |  |  |  | 0
Permits: Zoning, Building, Environmental, Other |  |  |  | 0 |  |  |  | 0
Survey |  |  |  | 0 |  |  |  | 0
Impact Fee |  |  |  | 0 |  |  |  | 0
Administrative Costs | [7 empty] | 0
Financing Costs |  |  |  | 0 |  |  |  | 0
Legal Fees |  |  |  | 0 |  |  |  | 0
Engineering Fees |  |  |  | 0 |  |  |  | 0
Other Fees |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
SITE PREP
Demolition (remodel) | ABC Remodeling | 1800 |  | 1800 | 1800 | 0 | 1800 | 0
Jacking & Shoring (remodel) | ABC Remodeling | 2500 | 750 | 3250 | 3550 | -300 |  | 3550
Dust control, surface protection (remodel) | ABC Remodeling | 600 | 450 | 1050 | 1200 | -150 | 600 | 600
Job-site access | NA |  |  | 0 |  |  |  | 0
Job-site security | NA |  |  | 0 |  |  |  | 0
Dumpster and removal | B&B Waste Management |  | 900 | 900 | 1350 | -450 | 900 | 450
Clear lot | NA |  |  | 0 |  |  |  | 0
Storage on site | NA |  |  | 0 |  |  |  | 0
Portable toilet | Poppy's Potties |  | 300 | 300 | 300 | 0 | 0 | 300
Temp power | NA |  |  | 0 |  |  |  | 0
Temp heat | NA |  |  | 0 |  |  |  | 0
Scaffolding rental | A-1 Rentals |  | 430 | 430 | 430 | 0 | 200 | 230
Tool/Equipment rental |  |  |  | 0 |  |  |  | 0
Other site prep |  |  |  | 0 |  |  |  | 0
Subtotal |  | 4900 | 2830 | 7730 | 8630 | -900 | 3500 | 5130
ON-SITE WATER/SEWER
Soil and perc tests |  |  |  | 0 |  |  |  | 0
Septic system design |  |  |  | 0 |  |  |  | 0
Septic permits, inspections, fees |  |  |  | 0 |  |  |  | 0
Septic system installation, tie in to house |  |  |  | 0 |  |  |  | 0
Dewatering (high water table) |  |  |  | 0 |  |  |  | 0
Well, pump, trenching, plumbing to house, pressure tank |  |  |  | 0 |  |  |  | 0
Well permits and fees |  |  |  | 0 |  |  |  | 0
Other utility expense |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
UTILITIES
Town Water: Tap fees and hookup |  |  |  | 0 |  |  |  | 0
Town Sewer: Tap fees and hookup |  |  |  | 0 |  |  |  | 0
Electrial: Permit, connection fee, hookup |  |  |  | 0 |  |  |  | 0
Gas: Permit, connection fee, installation |  |  |  | 0 |  |  |  | 0
LPN: Tank installation, hookup |  |  |  | 0 |  |  |  | 0
Oil tank installation |  |  |  | 0 |  |  |  | 0
Telecom hookup |  |  |  | 0 |  |  |  | 0
Other utility costs |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
EXCAVATION & EARTHWORK
Cut and fill |  |  |  | 0 |  |  |  | 0
Blasting |  |  |  | 0 |  |  |  | 0
Removal of stone/dirt |  |  |  | 0 |  |  |  | 0
Rough grading |  |  |  | 0 |  |  |  | 0
Trenching for utility hookups |  |  |  | 0 |  |  |  | 0
Foundation excavation |  |  |  | 0 |  |  |  | 0
Foundation footing drains |  |  |  | 0 |  |  |  | 0
Curtain drains |  |  |  | 0 |  |  |  | 0
Culverts |  |  |  | 0 |  |  |  | 0
Swales |  |  |  | 0 |  |  |  | 0
Retaining walls |  |  |  | 0 |  |  |  | 0
Ponds |  |  |  | 0 |  |  |  | 0
Other site drainage |  |  |  | 0 |  |  |  | 0
Backfill |  |  |  | 0 |  |  |  | 0
Compaction |  |  |  | 0 |  |  |  | 0
Top soil |  |  |  | 0 |  |  |  | 0
Finish grading |  |  |  | 0 |  |  |  | 0
Seeding/sod |  |  |  | 0 |  |  |  | 0
Other landscaping |  |  |  | 0 |  |  |  | 0
Other earthwork |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
FOUNDATION
Footings /pads |  |  |  | 0 |  |  |  | 0
Foundation walls/stem walls/grade beams |  |  |  | 0 |  |  |  | 0
Piers |  |  |  | 0 |  |  |  | 0
Slabs -- foundation, basement, garage |  |  |  | 0 |  |  |  | 0
Steel reinforcing |  |  |  | 0 |  |  |  | 0
Anchor bolts, hold downs |  |  |  | 0 |  |  |  | 0
Bulkheads |  |  |  | 0 |  |  |  | 0
Sub-slab vapor barrier |  |  |  | 0 |  |  |  | 0
Sump pump |  |  |  | 0 |  |  |  | 0
Sub-slab vapor barrier |  |  |  | 0 |  |  |  | 0
Crawlspace vapor barrier |  |  |  | 0 |  |  |  | 0
Crawlspace vents |  |  |  | 0 |  |  |  | 0
Foundation windows |  |  |  | 0 |  |  |  | 0
Damproofing, waterrproofing |  |  |  | 0 |  |  |  | 0
Foundation drain board |  |  |  | 0 |  |  |  | 0
Waterproofing/damproofing |  |  |  | 0 |  |  |  | 0
Slab insualtion: edge/below |  |  |  | 0 |  |  |  | 0
Exterior foundation insulation |  |  |  | 0 |  |  |  | 0
Exterior insulation coating/protection |  |  |  | 0 |  |  |  | 0
Other foundation |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
OTHER MASONRY/PAVING
Patios |  |  |  | 0 |  |  |  | 0
Exterior stairs |  |  |  | 0 |  |  |  | 0
Masonry chimneys |  |  |  | 0 |  |  |  | 0
Fireplaces/hearths |  |  |  | 0 |  |  |  | 0
Driveway |  |  |  | 0 |  |  |  | 0
Walkways |  |  |  | 0 |  |  |  | 0
Other masonry |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ROUGH FRAMING
Sill and seal |  |  |  | 0 |  |  |  | 0
Steel or wood carrying beam, lolly columns |  |  |  | 0 |  |  |  | 0
Floor framing |  |  |  | 0 |  |  |  | 0
Exterior and interior walls, rough stairs |  |  |  | 0 |  |  |  | 0
Sheathing, subflooring |  |  |  | 0 |  |  |  | 0
Roof framing/trusses |  |  |  | 0 |  |  |  | 0
Subfascia |  |  |  | 0 |  |  |  | 0
Steel framing connectors |  |  |  | 0 |  |  |  | 0
Nails, screws, fasteners |  |  |  | 0 |  |  |  | 0
Prep for plaster, drywall |  |  |  | 0 |  |  |  | 0
Other rough framing |  |  |  | 0 |  |  |  | 0
Rough framing, labor only |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ROOFING
Underlayment |  |  |  | 0 |  |  |  | 0
Membrane |  |  |  | 0 |  |  |  | 0
Flashing: chimney, vent pipes, sidewalls, other penetrations |  |  |  | 0 |  |  |  | 0
Drip Edge |  |  |  | 0 |  |  |  | 0
Roofing Installation |  |  |  | 0 |  |  |  | 0
Gutters and downspouts |  |  |  | 0 |  |  |  | 0
Skylights |  |  |  | 0 |  |  |  | 0
Ridge and roof vents |  |  |  | 0 |  |  |  | 0
Other roofing |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
EXTERIOR
Exterior foam sheathing |  |  |  | 0 |  |  |  | 0
Weather barrier (Tyvek, etc.) |  |  |  | 0 |  |  |  | 0
Membrane and flashing |  |  |  | 0 |  |  |  | 0
Vinyl or composite siding |  |  |  | 0 |  |  |  | 0
Wood siding |  |  |  | 0 |  |  |  | 0
Brick veneer |  |  |  | 0 |  |  |  | 0
Stone veneer |  |  |  | 0 |  |  |  | 0
Stucco |  |  |  | 0 |  |  |  | 0
Fascia, soffit, frieze, corner boards, water table |  |  |  | 0 |  |  |  | 0
Soffit/Gable vents |  |  |  | 0 |  |  |  | 0
Window/door trim |  |  |  | 0 |  |  |  | 0
Other exterior trim |  |  |  | 0 |  |  |  | 0
Exterior stairs, landing |  |  |  | 0 |  |  |  | 0
Exterior paint, stain, caulk |  |  |  | 0 |  |  |  | 0
Other exterior |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WINDOWS/EXTERIOR DOORS
Membrane & Flashing |  |  |  | 0 |  |  |  | 0
Exterior doors, prehung |  |  |  | 0 |  |  |  | 0
Exterior door slabs |  |  |  | 0 |  |  |  | 0
Exterior door frames, sills
Sidelights, transoms
Locksets, knobs, door hardware
Pation doors: sliding or hinged |  |  |  | 0 |  |  |  | 0
Windows |  |  |  | 0 |  |  |  | 0
Garage Doors & Opener
Other |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLUMBING
Drain/waste/vent |  |  |  | 0 |  |  |  | 0
Water supply piping |  |  |  | 0 |  |  |  | 0
Gas piping |  |  |  | 0 |  |  |  | 0
Water treatment |  |  |  | 0 |  |  |  | 0
Water heater |  |  |  | 0 |  |  |  | 0
Fixtures: toilets, tubs, sinks, showers |  |  |  | 0 |  |  |  | 0
Faucets, mixing valves, shower heads |  |  |  | 0 |  |  |  | 0
Disposal |  |  |  | 0 |  |  |  | 0
Other plumbing |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
ELECTRICAL
Service Panel, Sub-Panels |  |  |  | 0 |  |  |  | 0
Rough Wiring |  |  |  | 0 |  |  |  | 0
Phone, Cable, Internet Wiring |  |  |  | 0 |  |  |  | 0
Lighting Fixtures |  |  |  | 0 |  |  |  | 0
Low-Voltage Fixtures/transformers |  |  |  | 0 |  |  |  | 0
Exterior Lighting |  |  |  | 0 |  |  |  | 0
Devices: outlets, switches, dimmers |  |  |  | 0 |  |  |  | 0
Lighting control system |  |  |  | 0 |  |  |  | 0
Doorbell System |  |  |  | 0 |  |  |  | 0
Smoke, CO2 Alarms |  |  |  | 0 |  |  |  | 0
Intercom system |  |  |  | 0 |  |  |  | 0
Security system |  |  |  | 0 |  |  |  | 0
Home Theater/Entertainment |  |  |  | 0 |  |  |  | 0
Other electrical |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
HVAC
Furnace/Heat Pump |  |  |  | 0 |  |  |  | 0
Central AC |  |  |  | 0 |  |  |  | 0
Air handler |  |  |  | 0 |  |  |  | 0
Ductwork, grilles, registers |  |  |  | 0 |  |  |  | 0
Air filter |  |  |  | 0 |  |  |  | 0
Boiler, piping |  |  |  | 0 |  |  |  | 0
Radiators |  |  |  | 0 |  |  |  | 0
Whole-house ventilation (HRV, ERV, exhaust only, other) |  |  |  | 0 |  |  |  | 0
HVAC controls |  |  |  | 0 |  |  |  | 0
Solar hot water |  |  |  | 0 |  |  |  | 0
Other HVAC |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
INSULATION & AIR SEALING
Roof/attic insulation |  |  |  | 0 |  |  |  | 0
Roof/Eaves baffles |  |  |  | 0 |  |  |  | 0
Wall cavity insulation |  |  |  | 0 |  |  |  | 0
Foam board insulation |  |  |  | 0 |  |  |  | 0
Spray foam insulation |  |  |  | 0 |  |  |  | 0
Basement insulation (interior) |  |  |  | 0 |  |  |  | 0
Crawlspace insulation |  |  |  | 0 |  |  |  | 0
Air sealing |  |  |  | 0 |  |  |  | 0
Energy diagnostics (blower door, infrared) |  |  |  | 0 |  |  |  | 0
Other insulation |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
DRYWALL/PLASTER
Walls |  |  |  | 0 |  |  |  | 0
Ceilings, soffits |  |  |  | 0 |  |  |  | 0
Decorative plaster |  |  |  | 0 |  |  |  | 0
Drywall labor only |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERIOR FINISH
Interior Doors, prehung |  |  |  | 0 |  |  |  | 0
Interor Door slabs |  |  |  | 0 |  |  |  | 0
Interior Door frames, thresholds |  |  |  | 0 |  |  |  | 0
Door knobs, hardware |  |  |  | 0 |  |  |  | 0
Interior Trim: Baseboard, Casings, Crown, Chair Rail, Other |  |  |  | 0 |  |  |  | 0
Wainscotting, Paneling |  |  |  | 0 |  |  |  | 0
Built-In Shelving, Cabinets |  |  |  | 0 |  |  |  | 0
Closet Shelving, Hardware |  |  |  | 0 |  |  |  | 0
Stairs, Railings, Newels |  |  |  | 0 |  |  |  | 0
Interior Painting, Staining |  |  |  | 0 |  |  |  | 0
Wood Flooring |  |  |  | 0 |  |  |  | 0
Carpeting |  |  |  | 0 |  |  |  | 0
Resilient/Vinyl Flooring |  |  |  | 0 |  |  |  | 0
Ceramic Tile/Stone (& Underlayment, Surface Prep) |  |  |  | 0 |  |  |  | 0
Other Flooring |  |  |  | 0 |  |  |  | 0
Acoustical, Metal, Decorative Ceilings |  |  |  | 0 |  |  |  | 0
Interior Carpentry Labor Only |  |  |  | 0 |  |  |  | 0
Other Interior finish |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kitchen & Bath
Kitchen cabinets |  |  |  | 0 |  |  |  | 0
Bath cabinets |  |  |  | 0 |  |  |  | 0
Cabinet pulls, hardware |  |  |  | 0 |  |  |  | 0
Countertops, backsplash |  |  |  | 0 |  |  |  | 0
Ceramic tile, stone |  |  |  | 0 |  |  |  | 0
Raised tub platform |  |  |  | 0 |  |  |  | 0
Tub enclosure |  |  |  | 0 |  |  |  | 0
Shower doors/enclosure |  |  |  | 0 |  |  |  | 0
Medicine cabinets |  |  |  | 0 |  |  |  | 0
Mirrors |  |  |  | 0 |  |  |  | 0
Towel hangers, toilet-paper holders, accessories |  |  |  | 0 |  |  |  | 0
Other K&B |  |  |  | 0 |  |  |  | 0
K&B labor only |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Porches and Decks
Open porch |  |  |  | 0 |  |  |  | 0
Screened porch |  |  |  | 0 |  |  |  | 0
Wood or composite deck |  |  |  | 0 |  |  |  | 0
Fencing |  |  |  | 0 |  |  |  | 0
Other outdoor structures |  |  |  | 0 |  |  |  | 0
Porches and Decks labor only |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Appliances
Refrigerator |  |  |  | 0 |  |  |  | 0
Range, cooktop |  |  |  | 0 |  |  |  | 0
Microwave |  |  |  | 0 |  |  |  | 0
Range hood |  |  |  | 0 |  |  |  | 0
Dishwasher |  |  |  | 0 |  |  |  | 0
Washer/Dryer |  |  |  | 0 |  |  |  | 0
Other appliances |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL CONSTRUCTION COSTS |  | 4900 | 2830 | 7730 | 8630 | -900 | 3500 | 5130
Note: Add 20% to 25% for contractor’s overhead and profit, plus 8% for sales and marketing if purchased from a developer. © 2012 BuildingAdvisor LLC. All rights reserved.